## Overview
Time available
Number of weeks | 13
Group Members | 7
Hours Per Week/Group Member | 25
Total Hours Available | 2275
Planned Resource Allocation
Activity | Percentage | Hours | Start Week | End Week
Pre-implementation Research | 4.396% | 100 | 36 | 38
Planning | 4.396% | 100 | 36 | 39
Requirements Specification | 6.593% | 150 | 37 | 39
Design | 12.09% | 275 | 38 | 40
Implementation | 17.58% | 400 | 39 | 42
Documentation | 10.99% | 250 | 39 | 43
Evaluation/Testing | 13.19% | 300 | 41 | 44
Final Report | 17.58% | 400 | 44 | 47
Administrative Tasks | 13.19% | 300 | 36 | 47
Total | 100% | 2275
Gantt Chart
Activity | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47
Pre-implementation Research
Planning
Requirements Specification
Design
Implementation
Documentation
Evaluation/Testing
Final Report
Administrative Tasks

## Detailed Plan
Planned Resource Allocation
Activity | Percentage | Hours | Start Week | End Week | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47
Pre-implementation Research | 4.396% | 100 | 36 | 38 | 33.3333 | 33.3333 | 33.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Planning | 4.396% | 100 | 36 | 39 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Requirements Specification | 6.593% | 150 | 37 | 39 | 0 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design | 12.09% | 275 | 38 | 40 | 0 | 0 | 91.6667 | 91.6667 | 91.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implementation | 17.58% | 400 | 39 | 42 | 0 | 0 | 0 | 100 | 100 | 100 | 100 | 0 | 0 | 0 | 0 | 0
Documentation | 10.99% | 250 | 39 | 43 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0
Evaluation/Testing | 13.19% | 300 | 41 | 44 | 0 | 0 | 0 | 0 | 0 | 75 | 75 | 75 | 75 | 0 | 0 | 0
Final Report | 17.58% | 400 | 44 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100 | 100 | 100
Administrative Tasks | 13.19% | 300 | 36 | 47 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
Total | 100% | 2275 |  |  | 83.3333 | 133.3333 | 225 | 341.6667 | 266.6667 | 250 | 250 | 150 | 200 | 125 | 125 | 125
Cumulative Hours Worked |  |  |  |  | 83.3333 | 216.6667 | 441.6667 | 783.3333 | 1050 | 1300 | 1550 | 1700 | 1900 | 2025 | 2150 | 2275
Estimated Completion |  |  |  |  | 3.663% | 9.524% | 19.41% | 34.43% | 46.15% | 57.14% | 68.13% | 74.73% | 83.52% | 89.01% | 94.51% | 100%